| Progress Report of Project M:PR/E | Project No. : / |
| --- | --- |

Reporting Period: From ________________(month/year) to ________________(month/year)

Part A

Project Title: ____________________________________________________________________________

Name of Organization/School: ______________________________________________________________

Project Period: From _______________________(month/year) to __________________________(month/year)

Part B

Please read the Guidelines to Completion of Progress Report of Quality Education Fund Projects before completing this part of the report.

Please use separate A4-size sheets to report the progress with regard to the following aspects:

- Project activity during the reporting period

- Project variation*, if any, during the reporting period

- Self-evaluation of project effectiveness with indicators and measures of effectiveness clearly stipulated

- Dissemination of deliverables and good practices, if any, and responses to such dissemination

| Name of Project Leader: | _________________________ | Name of Grantee: | _________________________ |
| --- | --- | --- | --- |
| Signature: | _________________________ | Signature: | _________________________ |
| Date: | _________________________ | Date: | _________________________ |

* For variations not covered by the terms of the Agreement, a separate written application should be submitted to the Quality Education Fund for prior approval.

* Progress Report of Project should be submitted via “Electronic Project Management System” (EPMS).  Once submitted, these reports are regarded as already endorsed by the supervisor of the school/the head of the organization or the one who signed the Quality Education Fund Agreement for allocation of grant on behalf of the organization.

Guidelines to Completion of Progress Report of Quality Education Fund Projects

The Progress Report is intended to be an aid to reflection by Project Leaders on the implementation of the project.  Kindly study the following guidelines prior to the completion of the report and elaborate clearly on the four aspects described below.

# 1. Project activity

This section should cover:

- information on the dates, time, venues and number of participants of the activities held during the reporting period (the information may be presented in a table form)

- the percentage, in terms of key tasks, of the project completed at the end of the reporting period

  - Curriculum

  - AI & VR

Activity

| Date | Time | Venues | Number | Activities |
| --- | --- | --- | --- | --- |
| 12/10/2023 | 11 a.m. | Online meeting | 8 | Discussion of technical issues - Survey of speech recognition API used in the prototype system for deliverable 2 |
| 09/11/2023 | 10 a.m. | Online meeting | 7 | Discussion of technical issues - Design of the system - System concurrency - Delay of recognition API |
| 23/11/2023 | 10 a.m. | Online meeting | 7 | Discussion of technical issues - System design iteration |
| 07/12/2023 | 10 a.m. | Online meeting | 8 | Discussion of technical issues - Object detection for video recording - Details for IRB application |
| 04/01/2024 | 10 a.m. | Online meeting | 8 | Discussion of technical issues - Object detection for video recording - Issues about data protection |
| 18/01/2024 | 10 a.m. | Online meeting | 8 | Discussion of technical issues - Project milestone updating - System deployment |
| 01/02/2024 | 9 a.m. | Online meeting | 8 | Discussion of technical issues - Project milestone updating - System deployment |

Percentage

- Deliverable 2: VR software for immersive self-directed English-speaking program (10%)

- Deliverable 4: AI Feedback system for students’ speech analysis (30%)

  - LMS & Mobile Application

| Date | Venues | No. of attendee | Activities |
| --- | --- | --- | --- |
| 9/10/2023 10:30am | Online Meeting | 7 | Project kick start meeting. Discuss: - Timeline - Project infrastructure setup - Development flow |
| 12/10/2023 10:30am | Online Meeting | 4 | Project infrastructure setup - Prepare pricing quotation from Azure and AWS |
| 26/10/2023 11:30am | Online Meeting | 4 | Project infrastructure setup - Cloud service comparison from 2 different ISP Project specification document - 1st draft of functional specification - 1st draft of APP wireframe |
| 31/10/2023 10:00am | Online Meeting | 4 | Project infrastructure setup - Tendering process follow up (PURO) Project specification document - Gamification features |
| 6/11/2023 12:30pm | Online Meeting | 4 | Project infrastructure setup - Tendering process follow up (PURO) Project specification document - Research on mini-game for App |
| 29/11/2023 10:30am | Online Meeting | 4 | Project infrastructure setup - Final tendering process Project specification document - Finalizing project functional specification (learning_management_system) - System wireframe review |
| 4/12/2023 10:30 | Online Meeting | 4 | Project specification document - 2nd Draft project functional specification (learning_management_system) (reviewing by CLE IT team) System wireframe review |
| 13/12/2023 | Signoff | 2 | LMS functional specification signoff |
| 18/12/2023 10:30 | Online Meeting | 4 | Project infrastructure setup - Azure Cloud service setup (SoftwareOne) - Voice recognition research |
| 28/12/2023 | Online Meeting | 3 | Adhoc meeting in Cloud service setup |
| 4/1/2024 9:00am | Online Meeting | 8 | Project milestone update |
| 8/1/2024 10:30 | Online Meeting | 4 | LMS features discussion. - POC of voice recognition tool PM workflow discussion Project development platform subdomain application |
| 15/1/2024 10:30am | Online Meeting | 4 | Discussion on LMS and APP - Lesson structure - Course structure |
| 19/1/2024 2:30pm | Online Meeting | 3 | Project Setup training with AI/VR team. (redmine and gitlab) |
| 22/1/2024 10:30am | Online Meeting | 4 | Deliverable: LMS features walkthrough and feedback |
| 29/1/2024 10:30am | Online Meeting | 4 | LMS walkthrough and training for curriculum team. Project Setup training with curriculum team (redmine) |
| 5/2/2024 10:30am | Online Meeting | 4 | App features discussion: - New course structure |

Completion of key projects’ deliverables:

- System Specification Document (100%)

- LMS (Support curriculum management (module index: 1,2,3)) (100%)

- Project infrastructure setup (100%)

2. Project variation

This section should cover, where applicable, variations of project with details and justifications during the reporting period:

- changes in the schedule of the programme, including the activities cancelled, postponed or added

- details of the deviation from the proposal regarding the quantity and qualification of the staff hired for the project; staff turnover

- budget item reallocation

- change in project team composition

- other variations not mentioned above

Please state whether the above variations are able to solve the problems encountered.

  - Curriculum

  - AI & VR

Team composition:

- A postdoctoral fellow for project management

- A Ph.D. student and a research assistant for VR development

- A Ph.D. student and a research assistant for AI development

  - LMS & Mobile Application

Team composition:

- 1 Project Manager

- 2 frontend developers

- 2 backend developers

- 1 system engineer

- 1 graphic designer

# 3. Self-evaluation of project effectiveness

This section should evaluate the effectiveness of the project activities with regard to:

- attainment of the stated objectives

- success of the activities in the light of the impact on the participants

- resources (e.g. people, time and equipment, etc.) used for the activities

  - Curriculum

  - AI & VR

- We have attained the stated objectives as claimed in the proposal.

- The prototype system for curriculum testing has all established functions implemented and runs smoothly during the internal testing phase.

- The whole team collaborates efficiently. All issues are addressed within the schedule. Equipment, such as PC, VR helmets, and an online server are fully used for development.

  - LMS & Mobile Application

1) Objectives: All objectives were achieved, albeit with a 30-day delay due to issues with the AZURE cloud service vendor.

2) Impact on Participants: Successful project setup, team training, and User Acceptance Testing (UAT) of the Learning Management System (LMS) had a positive impact on participants. An additional Proof of Concept (POC) in the form of a voice recognition training tool was also developed during the resource blockage, which received positive feedback.

3) Resource Utilization: Despite challenges, resources were effectively managed, and the team demonstrated adaptability by developing the voice recognition training tool. Overall, the project effectively achieved its objectives, considering the circumstances and resource constraints.

# 4. Dissemination of deliverables and good practices

This section should cover, where applicable:

- tangible deliverables (e.g. CD ROMs, publications, etc.) at this stage

- dissemination activities such as experience-sharing sessions, distribution of deliverables or media interview held during the reporting period and the responses of the participants/recipients to such dissemination activities

- deliverables or good practices that are worthy of dissemination to the school sector at this stage and the mode in which these deliverables or good practices can be disseminated (e.g. workshop, seminar etc.)

Please enclose the tangible deliverables with this progress report.

  - Curriculum

  - AI & VR

- Deliverables: An online prototype for curriculum test.

- Mode: Online meeting for the prototype usage.

  - LMS & Mobile Application

Deliverables: System functional specification and Learning management system for curriculum development

Activities: Project infrastructure setup including platform (development environment), project applications (e.g. gitlab, redmine etc) and onboard training.